## Project Dashboard
Task | Start Date | End Date | Status | Assigned To | Budget (USD) | Cost to Date (USD)
Requirement Gathering | 2025-01-01 | 2025-01-10 | Completed | John Doe | 1000 | 950
Design Phase | 2025-01-11 | 2025-01-20 | Completed | Jane Smith | 1500 | 1450
Development | 2025-01-21 | 2025-02-15 | Ongoing | Dev Team | 5000 | 3200
Testing | 2025-02-16 | 2025-02-28 | Pending | QA Team | 2000 | 0
Deployment | 2025-03-01 | 2025-03-05 | Pending | Ops Team | 800 | 0